## Sheet1
Quiz App Tasks
Initial Tasks
Create Task List
Creat repo
Create file structure
Connect repo with sourcetree
Commit initial source
Functionality
Add timer
Research how to create different types
Create a timer to use for quiz app
Apply timer for each question
Help button
Modal design
Get click event
Setup fade in and fade out
JS objects
Create arrays
Questions
Answers
Create global variables
counter
Score percentage
User selection functionality
show user choices
show user answers
get click event of choice locations
get val of user choice
Next question
Don't show "next" button until click
on click-show next button
show correct answer
"Next" btn click
hide current question
show next question
Increment counter with each question
Counters
Initialize each to 0
Show counter and total
Final functions
Show score results
Get the end point
Show new game btn
HTML layout
Navbar
css includes
js includes
Quiz game section
Radio Buttons
Help modal section
Scoring section
CSS Styles
Button style
Section style
Modal style
Body style
Image sizes and alignment

## Sheet2
Quiz App Task List
| Projects |  |  |  |  | Deliverable(s) |  | Cost/Hours
Status | Priority | Deadline | Task | Assignee | Description | Deliverable | % Done | Fixed Cost | Est. Hrs | Actual Hrs
Project Name
 | High | 2015-08-27 | Task |  | details of task here |  | 100% | 0
 | High | 2015-08-27 | Task |  |  |  | 50% | 0
☐ | Low | 2016-07-18 | Task |  |  |  | 0% | 0
Project Name
☐
☐
☐
☐
Project Name
☐
☐
☐
☐
Project Name
☐
☐
☐
☐
Project Name